## Project_Info
Project Name: | DEPI Final Project ( E-commerce testing )
Client: | DEPI
Created By: | Team 49 ( Mohamed Asharf / Mariam Farghl / Shaker Nassry / Mariam Isaac / Ereny Andro )
Creation Date: | 2025-10-28
Reviewed by: | Team 49 ( Mohamed Asharf / Mariam Farghl / Shaker Nassry / Mariam Isaac / Ereny Andro )
Type of Testing: | ( Full Funcional / non-Funcional / API / Automation )

## Requirements
Req_ID | Description | Type | Priority | Status | Version
Mariam Isaac
REQ_AUTH_001 | User shall be able to create an account by providing required details and receive a confirmation message or email. | Functional | High | v1.1 | Approved
REQ_AUTH_002 | Registered users shall be able to log in using valid credentials and access their dashboard. | Functional | High | v1.1 | Approved
REQ_AUTH_003 | System shall allow users to reset forgotten passwords by sending a secure reset link via email. | Functional | Medium | v1.1 | Approved
REQ_AUTH_004 | System shall display past orders with details such as order ID, date, items, and status. | Functional | Medium | v1.1 | Approved
REQ_AUTH_005 | Logged-in users shall be able to update their address and change their password securely. | Functional | Medium | v1.1 | Approved
REQ_AUTH_006 | Registration and Login pages shall have an intuitive design with clear labels and validation messages. | Usability | Low | v1.1 | Approved
REQ_AUTH_007 | Authentication forms shall use HTTPS, encrypted passwords, and protect against common security vulnerabilities. | Security | High | v1.1 | Approved
Ereny Andro
REQ_PROD_008 | Homepage shall correctly display all branded sections, categories, and featured items. | Functional | High | v1.1 | Approved
REQ_PROD_009 | Users shall be able to navigate smoothly between product categories with no broken links or delays. | Functional | High | v1.1 | Approved
REQ_PROD_010 | Product listing pages shall display accurate product information, including name, image, price, and key details. | Functional | High | v1.1 | Approved
REQ_PROD_011 | The system shall allow sorting of products by price, name, or specifications. | Functional | Medium | v1.1 | Approved
REQ_PROD_012 | The system shall support product filtering based on attributes (e.g., price range, brand, specifications). | Functional | High | v1.1 | Approved
REQ_PROD_013 | Users shall be able to toggle product listing view between Grid and List layouts. | Functional | Medium | v1.1 | Approved
REQ_PROD_014 | The global search bar shall accept queries by product name, category, and brand. | Functional | High | v1.1 | Approved
REQ_PROD_015 | Search results shall accurately match entered keywords and display relevant products. | Functional | High | v1.1 | Approved
REQ_PROD_016 | Product detail page shall display complete information including product description, multiple images, and price. | Functional | High | v1.1 | Approved
Mariam Farghl
REQ_CART_017 | Users shall be able to specify a product quantity and add items to the shopping cart directly from the product details page. | Functional | High | v1.1 | Approved
REQ_CART_018 | After adding a product to the cart, a confirmation pop-up or modal shall appear with options to “View Cart” or “Continue Shopping.” | Functional | Medium | v1.1 | Approved
REQ_CART_019 | Users shall be able to view their shopping cart contents at any time by clicking the Cart button in the header section. | Functional | High | v1.1 | Approved
REQ_CART_020 | The cart page shall display each product as a line item showing its image, description, price, quantity, and line total. | Functional | High | v1.1 | Approved
REQ_CART_021 | The cart page shall correctly calculate and display the total price for all items in the cart. | Functional | High | v1.1 | Approved
REQ_CART_022 | Users shall be able to remove items completely from the shopping cart using a Remove (X) button beside each item. | Functional | Medium | v1.1 | Approved
REQ_CART_023 | The shopping cart contents for guest users shall persist throughout the browsing session, even if the user navigates away and returns. | Functional | Medium | v1.1 | Approved
REQ_CART_024 | Users shall be able to proceed to the checkout process from the cart page using a Proceed to Checkout button. | Functional | High | v1.1 | Approved
REQ_CART_025 | When a guest user clicks Proceed to Checkout, the system shall prompt them to Register or Login before continuing. | Functional | Medium | v1.1 | Approved
REQ_CART_026 | The checkout page shall display the user’s delivery and billing address details for confirmation before placing the order. | Functional | High | v1.1 | Approved
REQ_CART_027 | The checkout page shall include a summary section titled “Review Your Order” listing all ordered items and their totals. | Functional | Medium | v1.1 | Approved
REQ_CART_028 | Users shall be able to add comments or special instructions for their order in a designated text area before placing the order. | Functional | Low | v1.1 | Approved
REQ_CART_029 | Upon clicking Place Order, users shall be redirected to the Payment page. | Functional | High | v1.1 | Approved
REQ_CART_030 | The payment page shall allow users to enter dummy payment information including Name on Card, Card Number, CVC, Expiration Month, and Year. | Functional | High | v1.1 | Approved
REQ_CART_031 | After submitting payment details, the system shall display an order confirmation message: “Your order has been placed successfully!” | Functional | High | v1.1 | Approved
REQ_CART_032 | The system shall provide users with an option to download an invoice for the successfully placed order. | Functional | Medium | v1.1 | Approved
Shaker Nassry
REQ_ADMIN_033 | The system shall allow an admin to create new products by entering all required fields such as name, price, SKU, category, manufacturer, and image. | Functional | High | v1.1 | Approved
REQ_ADMIN_034 | The system shall allow an admin to view all existing products in the catalog with full details displayed accurately. | Functional | High | v1.1 | Approved
REQ_ADMIN_035 | The system shall allow an admin to update existing product information, including name, price, image, and inventory quantity. | Functional | High | v1.1 | Approved
REQ_ADMIN_036 | The system shall allow an admin to delete products from the catalog with confirmation to prevent accidental deletion. | Functional | High | v1.1 | Approved
REQ_ADMIN_037 | The system shall validate mandatory fields on the Add/Edit Product page and display appropriate error messages for missing or invalid input. | Functional | Medium | v1.1 | Approved
REQ_ADMIN_038 | The system shall maintain synchronization and data consistency between the backend catalog and the frontend product listings. | Functional | High | v1.1 | Approved
REQ_ADMIN_039 | The admin dashboard shall display accurate counts and statistics for products, categories, and manufacturers in real-time. | Functional | High | v1.1 | Approved
REQ_ADMIN_040 | Dashboard metrics shall update automatically after Create, Read, Update, or Delete (CRUD) operations are performed on catalog items. | Functional | High | v1.1 | Approved
Mohamed Asharf
REQ_NFR_041 | The website shall achieve a Largest Contentful Paint (LCP) of under 3 seconds on standard broadband connections for all major pages. | Performance | High | v1.1 | Approved
REQ_NFR_042 | The product search functionality shall return results within 2 seconds for typical user queries under standard network conditions. | Performance | High | v1.1 | Approved
REQ_NFR_043 | The average server response time for API requests shall be below 500 ms under normal load conditions. | Performance | High | v1.1 | Approved
REQ_NFR_044 | The website shall maintain a consistent and intuitive navigation structure (header, footer, sidebars) across all pages. | Usability | High | v1.1 | Approved
REQ_NFR_045 | All interactive components (e.g., buttons, links, input fields) shall be visually identifiable and provide real‑time feedback on interaction such as hover, focus, or click states. | Usability | Medium | v1.1 | Approved
REQ_NFR_046 | The website layout shall be fully responsive, maintaining correct functionality and display across standard desktop (1920×1080), tablet (768×1024), and mobile (375×667) resolutions. | Usability | High | v1.1 | Approved
REQ_NFR_047 | Validation error messages shall be clear, specific, and displayed adjacent to the related input field for all forms. | Usability | High | v1.1 | Approved
REQ_NFR_048 | The website shall comply with WCAG 2.1 Level AA accessibility standards, including color contrast ratios and keyboard‑based navigation. | Usability / Accessibility | High | v1.1 | Approved
REQ_NFR_049 | All communications between client and server shall be encrypted via HTTPS using a valid TLS certificate at all times. | Security | High | v1.1 | Approved
REQ_NFR_050 | The application shall be hardened against common web vulnerabilities, including but not limited to XSS, SQL Injection, and CSRF attacks. | Security | High | v1.1 | Approved
REQ_NFR_051 | The website shall operate correctly on the latest stable versions of major browsers: Google Chrome, Mozilla Firefox, Safari, and Microsoft Edge. | Compatibility | High | v1.1 | Approved
REQ_NFR_052 | All core website functionalities shall work correctly when JavaScript is enabled, without causing script errors or feature malfunction. | Compatibility | High | v1.1 | Approved

## User_Stories
US_ID | Req_ID | UserStory | AcceptanceCriteria
Mariam Isaac
US_001 | REQ_AUTH_001 | As a new user, I want to register by providing my details so that I can create an account and start using the platform. | - User can successfully register with all required fields completed.
- System displays a success message and/or sends a confirmation email after registration.
- Registration fails gracefully if mandatory fields are missing or invalid.
US_002 | REQ_AUTH_002 | As a registered user, I want to log in using valid credentials so that I can access my account securely. | - User can log in using valid email/username and password.
- User is redirected to the My Account page upon success.
- Invalid credentials display an error message without exposing sensitive details.
US_003 | REQ_AUTH_003 | As a user who forgot my password, I want to reset it easily so I can regain access to my account. | - User can request a password reset by providing their registered email.
- A reset link is sent to the correct email address.
- The link allows the user to set a new password successfully.
US_004 | REQ_AUTH_004 | As a logged-in user, I want to view my past orders so that I can check my purchase history. | - User can view a list of all previous orders with basic details (order ID, date, amount, status).
- Orders are displayed correctly and sorted (e.g., most recent first).
- No orders message shown if history is empty.
US_005 | REQ_AUTH_005 | As a logged-in user, I want to update my address and password so that my account information stays current. | - User can edit and save new address and password details successfully.
- System validates all required fields.
- Confirmation message is displayed after successful changes.
US_006 | REQ_AUTH_006 | As a user, I want the registration and login forms to be simple and intuitive so that I can complete them easily. | - Form labels and field names are clear and descriptive.
- Error messages appear when invalid data is entered.
- Page layout and navigation are intuitive and accessible.
US_007 | REQ_AUTH_007 | As a user, I want the authentication forms to be secure so that my personal data is protected. | - Passwords are masked when typed.
- Passwords must meet defined complexity rules.
- All data is transmitted securely via HTTPS.
- System prevents common security issues (e.g., SQL injection, XSS).
Ereny Andro
US_008 | REQ_PROD_008 | As a visitor, I want to see all main elements on the homepage so that I can easily explore the site and featured items. | - Homepage displays all key sections: brands, categories, navigation bar, and featured items.
- Elements load correctly without layout or display issues.
- No broken links or missing visuals.
US_009 | REQ_PROD_009 | As a shopper, I want to browse through product categories so that I can find items under specific sections. | - Category navigation works smoothly with no broken links.
- Clicked categories show correct, relevant product listings.
- Breadcrumb navigation updates accurately.
US_010 | REQ_PROD_010 | As a customer, I want to view product information (name, image, price, short details) so that I can make purchasing decisions. | - Product listings show correct product name, image, and price.
- Data displayed matches backend records.
- No missing or distorted product details.
US_011 | REQ_PROD_011 | As a user, I want to sort products by price or specifications so that I can compare options easily. | - Sorting options available (Low→High, High→Low, Specs).
- Sorted results update dynamically.
- Sorting maintains accuracy and stability.
US_012 | REQ_PROD_012 | As a user, I want to filter products by brand, price, and specifications so that I can narrow down my search. | - Filter options functional and responsive.
- Filters update the product list instantly.
- Multiple filters can be applied simultaneously.
US_013 | REQ_PROD_013 | As a user, I want to switch between grid and list views so that I can view products in my preferred layout. | - Grid/List toggle buttons visible and operational.
- Selected layout updates instantly.
- Layout preference remains consistent during navigation.
US_014 | REQ_PROD_014 | As a user, I want to search for products by name, category, or brand so that I can quickly find what I need. | - Search bar accepts input and retrieves relevant results.
- Results are displayed accurately without delay.
- No unrelated products appear.
US_015 | REQ_PROD_015 | As a user, I want accurate search results so that I don’t waste time reviewing unrelated items. | - Displayed results match entered keywords accurately.
- Results ranked by relevance.
- No duplicate or irrelevant items.
US_016 | REQ_PROD_016 | As a customer, I want to open a product detail page so that I can view complete product information and reviews. | - Product detail page shows full data (name, price, description, images).
- Reviews and ratings load correctly.
- Layout remains responsive and error-free.
Mariam Farghl
US_017 | REQ_CART_017 | As a user, I want to specify a quantity and add a product to my cart so that I can purchase multiple items at once. | - Users can set item quantity before adding to cart.
- Selected item and quantity appear correctly in the cart.
- Confirmation message indicates successful addition.
US_018 | REQ_CART_018 | As a user, I want to see a confirmation pop-up after adding a product so that I can decide to continue shopping or view my cart. | - Upon adding a product, a confirmation modal appears.
- Modal includes options to “View Cart” and “Continue Shopping.”
- Selecting an option executes the corresponding action.
US_019 | REQ_CART_019 | As a user, I want to view my shopping cart by clicking the “Cart” button so that I can see what I’ve added. | - Clicking “Cart” redirects to the cart page.
- Cart page shows all added products with correct details.
US_020 | REQ_CART_020 | As a user, I want to see each product in my cart with its image, description, price, quantity, and total price. | - Each item appears as a distinct line item.
- All details (image, price, description, total) are displayed accurately.
US_021 | REQ_CART_021 | As a user, I want to see the updated total price automatically so that I know the total cost before checkout. | - The total price updates automatically based on product quantity × price.
- Price calculation remains correct after item adjustments.
US_022 | REQ_CART_022 | As a user, I want to remove products from my cart easily so that I can update my order conveniently. | - Clicking the “Remove (X)” button deletes that product immediately.
- Cart total updates correctly after item removal.
US_023 | REQ_CART_023 | As a guest user, I want my cart contents to persist within the same session so that I don’t lose items while browsing. | - Cart retains all added products during the same session.
- Items reappear even after navigating to other pages.
US_024 | REQ_CART_024 | As a user, I want to proceed to the checkout page so that I can complete my purchase. | - “Proceed to Checkout” button redirects to the checkout page.
- Page loads successfully with the user’s order overview.
US_025 | REQ_CART_025 | As a guest user, I want to be prompted to log in or register before accessing checkout so that only registered users can confirm orders. | - A modal appears prompting login or registration on “Proceed to Checkout.”
- User redirected based on choice.
US_026 | REQ_CART_026 | As a user, I want to confirm my delivery and billing address details on checkout so that my order goes to the correct destination. | - Checkout page displays saved addresses.
- Users can verify or edit address information.
US_027 | REQ_CART_027 | As a user, I want to review my order summary before finalizing my purchase. | - The “Review Your Order” section lists products, quantities, and prices.
- Totals appear accurate.
US_028 | REQ_CART_028 | As a user, I want to add comments or delivery instructions to my order before placing it. | - A text box is available to add notes or instructions.
- Data is saved and sent with the order.
US_029 | REQ_CART_029 | As a user, I want to be redirected to the payment page after clicking “Place Order.” | - Clicking “Place Order” leads to the payment page successfully.
- Page loads all required payment fields.
US_030 | REQ_CART_030 | As a user, I want to enter dummy payment information to simulate a purchase without real transactions. | - Payment form accepts standard input fields (Name, Card, CVC, Expiration Date).
- Data validation works correctly.
US_031 | REQ_CART_031 | As a user, I want to see an order confirmation message once my payment is successfully processed. | - Confirmation message “Your order has been placed successfully!” displays after payment submission.
- Order record generated.
US_032 | REQ_CART_032 | As a user, I want to download an invoice for my completed order. | - “Download Invoice” button generates accurate invoice.
- File downloads in PDF format with correct details (items, totals, user).
Shaker Nassry
US_033 | REQ_ADMIN_033 | As an admin, I want to add new products so that I can manage the catalog efficiently. | - Given the admin is logged in, when all mandatory fields (name, price, SKU, category, manufacturer, image) are filled and “Save” is clicked, then a new product is created successfully.
- The product appears in both the admin catalog and frontend listing.
US_034 | REQ_ADMIN_034 | As an admin, I want to view detailed product information so that I can verify catalog accuracy. | - Given the admin is on the catalog page, when they click “View” on a product, then full product details (name, price, image, stock, category) are displayed accurately.
US_035 | REQ_ADMIN_035 | As an admin, I want to edit product information so that I can correct or update data when necessary. | - Given the admin selects a product, when they update one or more fields and click “Save,” then the catalog refreshes and shows updated details both in admin and frontend views.
US_036 | REQ_ADMIN_036 | As an admin, I want to delete a product so that I can remove discontinued or obsolete items. | - Given the admin clicks “Delete,” when the action is confirmed, then the selected product is permanently removed from the catalog and no longer visible on the frontend.
US_037 | REQ_ADMIN_037 | As an admin, I want to see validation messages when mandatory fields are missing or invalid so that I know what to fix. | - Given any required field is left blank or entered incorrectly, when the admin clicks “Save,” then a validation message appears next to the affected field explaining the issue.
US_038 | REQ_ADMIN_038 | As an admin, I want backend changes to automatically reflect on the frontend product listings so that users see the most current data. | - Given the admin updates product data (price, image, or stock), when viewing the same product on the frontend, then all changes display immediately and consistently.
US_039 | REQ_ADMIN_039 | As an admin, I want to view accurate product, category, and manufacturer statistics on the dashboard so that I can monitor operations efficiently. | - Given normal operations occur, when the admin opens the dashboard, then metrics (e.g., product count, categories, manufacturers) display correct values reflecting current catalog data.
US_040 | REQ_ADMIN_040 | As an admin, I want dashboard metrics to auto-refresh after catalog changes so that I always see updated statistics. | - Given a product is added, updated, or deleted, when the admin revisits the dashboard, then all associated counts and graphs update dynamically.
Mohamed Asharf
US_041 | REQ_NFR_041 | As a user, I want all website pages to load quickly so that I can browse without delays. | Homepage and key pages achieve LCP ≤ 3 seconds on standard broadband.
Pages render fully without noticeable layout shift (CLS ≈ 0).
US_042 | REQ_NFR_042 | As a customer, I want product search results to appear almost instantly so that I can find items faster. | Search results load within ≤ 2 seconds for typical queries.
Search consistently returns accurate, relevant product listings.
US_043 | REQ_NFR_043 | As a technical stakeholder, I want API responses to be fast so that page interactions remain smooth and responsive. | Server API response time is ≤ 500 ms under normal load.
No API endpoints cause delays or observable UI lag.
US_044 | REQ_NFR_044 | As a site visitor, I want consistent and intuitive navigation so that I can easily locate important pages. | Header, footer, and sidebar menus are identical across all pages.
Navigation links accurately direct to the intended sections.
US_045 | REQ_NFR_045 | As a user, I want clear visual cues for interactive elements so that I can understand where to click or tap. | Hover and focus states are visible for all interactive elements (buttons, links, inputs).
All interactive elements meet color‑contrast accessibility standards.
US_046 | REQ_NFR_046 | As a shopper, I want the site layout to adapt correctly on every device so I can browse comfortably anywhere. | Layout is fully responsive on desktop (1920×1080), tablet (768×1024), and mobile (375×667).
Interface remains readable with no overlapping or truncated elements.
US_047 | REQ_NFR_047 | As a visitor, I want clear and descriptive validation messages so that I can fix input errors easily. | Each invalid or missing field displays a clear error message next to it.
Error text uses accessible color contrast and provides specific guidance.
US_048 | REQ_NFR_048 | As a user with disabilities, I want the site to meet accessibility standards so I can navigate and use it independently. | All functions are usable via keyboard with logical tab sequences.
The site satisfies WCAG 2.1 AA standards for color contrast, ARIA labels, and alt text.
US_049 | REQ_NFR_049 | As a user, I want my connection to be secure so that my personal and financial data are protected. | The site uses HTTPS/TLS encryption for all pages.
No mixed‑content (HTTP) warnings appear in the browser.
US_050 | REQ_NFR_050 | As an admin, I want the system protected from malicious inputs so that it remains secure and stable. | The application prevents common attacks such as XSS, SQL Injection, and CSRF.
Invalid or unexpected input is handled gracefully without breaking the system.
US_051 | REQ_NFR_051 | As a customer, I want the website to function properly on all supported browsers so that I can shop on any platform. | The website works correctly on Chrome, Edge, Firefox, and Safari latest stable versions.
No layout distortions or missing elements appear.
US_052 | REQ_NFR_052 | As a user, I want all dynamic content and interactive features to work seamlessly with JavaScript enabled. | Core features (e.g., Add to Cart, Checkout) function without console errors.
Dynamic updates occur correctly without requiring full page reload.

## Test_Cases
TC_ID | Feature | Req ID | Title | Description | Preconditions | Test Steps | Test Data | Expected Result | Postconditions | Actual Result | Status | Priorty
Mariam Isaac
TC_001 | Registration | REQ_AUTH_001 | Verify valid registration | Validate that a user can successfully register using valid inputs. | User is on the Signup page. | 1. Open browser and go to https://automationexercise.com. | Name: Mariam | User account is created successfully and redirected to Account page. | User is logged in. | As expected. | Passed | High
[6 empty] | 2. Click Signup / Login. | Email: test123@mail.com
[6 empty] | 3. Enter a valid name and email in the “New User Signup” section. | Password: Abcd@123
4. Click Signup.
5. Fill in all mandatory fields (e.g., password, address, country).
6. Click Create Account.
7. Verify system displays success message and user is redirected to the “Account Created” page.
TC_002 | Registration | REQ_AUTH_001 | Verify invalid email format during registration | Validate error message when registering with an invalid email format. | User is on the Signup page. | 1. Navigate to Signup / Login. | Email: test123@ | System shows an error for invalid email format. Form is not submitted. | User remains on Signup page. | Error shown correctly. | Passed | Medium
2. Enter a valid name and invalid email (e.g., test123@).
3. Click Signup.
4. Verify an error message is displayed for invalid email format.
TC_003 | Registration | REQ_AUTH_001 | Verify duplicate email registration | Ensure registration with an already registered email displays a proper error message. | An existing user account is already registered. | 1. Go to Signup / Login. | Email: existing@mail.com | System displays duplicate email warning; registration is not allowed. | No new account created. | As expected. | Passed | Medium
2. Enter a valid name and an existing email.
3. Click Signup.
4. Verify an error message “Email Address already exists” appears.
TC_004 | Login | REQ_AUTH_002 | Verify valid login | Validate that a registered user can log in using correct credentials. | User account is registered. | 1. Open https://automationexercise.com. | Email: test123@mail.com | User successfully logs in and is redirected to My Account. | User is logged in. | As expected. | Passed | High
[6 empty] | 2. Click Signup / Login. | Password: Abcd@123
3. Enter valid email and password.
4. Click Login.
5. Verify redirection to My Account page.
TC_005 | Login | REQ_AUTH_002 | Verify invalid login credentials | Ensure system shows an error for invalid login credentials. | User account exists. | 1. Navigate to Signup / Login. | Email: fake@mail.com | “Your email or password is incorrect” message displayed; login fails. | User remains on login page. | As expected. | Passed | Medium
[6 empty] | 2. Enter invalid email or incorrect password. | Password: wrong
3. Click Login.
4. Observe displayed error message.
TC_006 | Forgot Password | REQ_AUTH_003 | Verify valid password reset process | Check password reset email functionality for valid users. | User has registered email. | 1. Go to Signup / Login. | Email: test123@mail.com | Password reset email is sent successfully. | User can reset password via received link. | Currently not implemented; no reset email sent. | Fail | High
2. Click Forgot Password link (if implemented).
3. Enter valid registered email.
4. Submit form.
5. Verify that password reset link email is received.
TC_007 | Forgot Password | REQ_AUTH_003 | Verify unregistered email reset attempt | Ensure helpful message appears when user enters unregistered email for reset. | None. | 1. Navigate to Signup / Login. | Email: none@mail.com | System displays “Email not found” and does not send any email. | No password reset triggered. | No clear “Email not found” message displayed. | Fail | Medium
2. Click Forgot Password link.
3. Enter an unregistered email.
4. Submit the form.
5. Verify if an appropriate message appears.
TC_008 | My Account | REQ_AUTH_004 | Verify order history display | Validate that user can view order history correctly. | User logged in with previous orders. | 1. Log in to user account. | Account with previous orders. | Order list and details displayed correctly. | Orders visible in My Account. | As expected. | Passed | Medium
2. Go to My Account → Orders.
3. Verify orders list is displayed with valid data.
TC_009 | My Account | REQ_AUTH_005 | Verify address update | Confirm user can update account address successfully. | User logged in. | 1. Log in. | New Address: 123 Test St, Cairo, Egypt | Address updated successfully and shown in account. | Updated address saved. | As expected. | Passed | Medium
2. Navigate to My Account → Addresses.
3. Click Edit, update details, and click Save.
4. Verify success message and updated data.
TC_010 | My Account | REQ_AUTH_005 | Verify password change | Validate that user can change password successfully. | User logged in. | 1. Navigate to My Account → Change Password (if available). | Old: Abcd@123 | Password updated successfully and new password works. | User logs in with new password. | Feature unavailable on site. | Fail | High
[6 empty] | 2. Enter current and new password. | New: Xyz@1234
3. Save changes.
4. Attempt to log in with new password.
TC_011 | Usability | REQ_AUTH_006 | Verify registration form layout | Ensure form fields and labels are properly aligned and visible. | User on Signup page. | 1. Navigate to Signup / Login. | N/A | All fields properly aligned with visible labels. | UI consistent. | As expected. | Passed | Low
2. Observe field alignment and label placement.
3. Verify form is user-friendly and visually consistent.
TC_012 | Usability | REQ_AUTH_006 | Verify button labeling | Check that form buttons are clearly labeled. | User on Login/Signup page. | 1. Go to Signup / Login. | N/A | Buttons labeled clearly and consistently. | UI consistent. | As expected. | Passed | Low
2. Observe buttons on both forms.
3. Verify labels (e.g., “Login”, “Signup”, “Create Account”) match intended actions.
TC_013 | Security | REQ_AUTH_007 | Verify password masking | Ensure password fields mask input characters. | Signup/Login page open. | 1. Open Signup / Login page. | Password: Test@123 | Password input masked by default. | UI functional. | As expected. | Passed | High
2. Type password in the field.
3. Ensure input is masked (dots/asterisks).
TC_014 | Security | REQ_AUTH_007 | Verify restricted access to My Account | Ensure My Account cannot be accessed without login. | User logged out. | 1. Log out of account. | N/A | Unauthorized users redirected to Login page. | Account access blocked. | As expected. | Passed | High
2. Manually navigate to My Account URL.
3. Press Enter.
4. Verify redirection to login page.
TC_015 | Security | REQ_AUTH_007 | Verify SQL injection prevention | Confirm login form rejects SQL injection attempts. | User on Login page. | 1. Go to Signup / Login. | Email: ' OR 1=1; -- | System rejects input and displays error safely. | Access restricted. | As expected. | Passed | High
[6 empty] | 2. Enter ' OR 1=1; -- as email. | Password: anything
3. Enter any password.
4. Click Login.
5. Verify login fails and no unauthorized access occurs.
Ereny Andro
TC_016 | Product Homepage | REQ_PROD_008 | Verify homepage elements load correctly | Validate homepage displays all UI elements such as brands, categories, and featured products without errors. | User is on homepage. | 1. Launch website. | N/A | Homepage displays all sections properly with no missing visuals or broken links. | Homepage loaded successfully. | Homepage elements display correctly. | Passed | High
2. Observe homepage elements (brands, categories, featured items).
TC_017 | Category Navigation | REQ_PROD_009 | Verify category navigation functionality | Ensure each category navigation link redirects to the correct product listing page. | Homepage loaded. | 1. Click on a product category from the navigation bar. | Category name | Category page opens showing correct product listings. | Category page successfully loaded. | Category page opens with expected items. | Passed | High
2. Observe displayed products.
TC_018 | Product Listing | REQ_PROD_010 | Verify product info on listing pages | Validate product listings display correct product details including name, image, add-to-cart, and view options. | Category page open. | 1. Open a category. | Category name | Each product card correctly shows name, image, and relevant options. | Products visible with accurate data. | Product data displayed correctly on listing. | Passed | High
2. Check multiple product cards.
3. Verify displayed name, image, and add-to-cart/view product buttons.
TC_019 | Product Sorting | REQ_PROD_011 | Verify product sorting by price (Low → High) | Validate product sorting feature arranges products by ascending price. | Product listing page open. | 1. Open any product category. | Products with varied prices. | Products appear sorted from lowest to highest price. | Product order updates instantly. | Sorting option not available. | Failed | Medium
2. Select sorting option “Price: Low → High”.
3. Verify product order updates correctly.
TC_020 | Product Sorting | REQ_PROD_011 | Verify product sorting by price (High → Low) | Validate product sorting feature arranges products by descending price. | Product listing page open. | 1. Open any product category. | Products with varied prices. | Products appear sorted from highest to lowest price. | Product order updates instantly. | Sorting option not available. | Failed | Medium
2. Select sorting option “Price: High → Low”.
3. Verify displayed product order.
TC_021 | Product Filtering | REQ_PROD_012 | Verify filtering by price range | Validate that users can filter product results by selected price range. | Product listing page open. | 1. Open a category page. | Price range: 200–500 | Only products within selected price range are displayed. | Product list updates according to filter. | Price filtering not implemented. | Failed | Medium
2. Select a price range (e.g., 200–500).
3. Observe displayed products.
TC_022 | Product Filtering | REQ_PROD_012 | Verify filtering by brand | Validate that users can filter products by brand name. | Product listing page open. | 1. Open category page. | Brand: Polo | Only products from the selected brand are displayed. | Filter applied successfully. | Brand filter applied correctly. | Passed | Medium
2. Select a brand filter (e.g., “Polo”).
3. Observe displayed results.
TC_023 | Product Layout | REQ_PROD_013 | Verify view switch between Grid and List | Validate that user can switch between Grid and List views without layout issues. | Product listing page open. | 1. Open category page. | N/A | Grid view: multi-column layout. | Selected view updates instantly. | Grid/List toggle unavailable. | Failed | Low
[6 empty] | 2. Click List View. |  | List view: single-column layout.
3. Click Grid View.
4. Compare layout changes.
TC_024 | Search | REQ_PROD_014 | Verify search by product name | Validate search functionality retrieves products by name. | Homepage loaded. | 1. Type “Blue top” in search bar. | Product: “Blue top” | Products named “Blue top” are displayed. | Search results visible. | Products displayed correctly. | Passed | Medium
2. Click Search.
TC_025 | Search | REQ_PROD_014 | Verify search by category | Validate search returns products when category name is entered. | Homepage loaded. | 1. Type “Jeans” in search bar. | Category: Jeans | Products belonging to “Jeans” category are displayed. | Search results visible. | Correct category results displayed. | Passed | Medium
2. Click Search.
TC_026 | Search | REQ_PROD_014 | Verify search by brand | Validate search displays matching products when brand name is entered. | Homepage loaded. | 1. Type “Polo” in search bar. | Brand: Polo | All “Polo”-branded products displayed. | Search results visible. | Not all “Polo” products shown. | Failed | Medium
2. Click Search.
TC_027 | Search Accuracy | REQ_PROD_015 | Verify accurate search results | Validate that search returns precise or “No results” when invalid keywords are entered. | Homepage loaded. | 1. Enter “abcxyz” in search bar. | Text: “abcxyz” | “No products found” message is displayed. | Message displayed to user. | No message shown, but no products visible. | Failed | Medium
2. Click Search.
TC_028 | Product Detail | REQ_PROD_016 | Verify product detail page loads correctly | Validate that product detail page displays complete and accurate product information. | Product listing visible. | 1. Click on any product (e.g., “Blue top”). | Product: “Blue top” | Product detail page loads with all required information and formatted correctly. | Product details visible. | Product info displayed correctly. | Passed | High
2. Review product name, availability, condition, brand, price, and images.
3. Check description and rating/reviews if available.
Mariam Farghl
TC_029 | Cart | REQ_CART_017 | Add single product to cart | Verify the user can add a product to the cart from the product details page with correct price and quantity. | User is on the product detail page. | 1. Open product detail page. | Product: Blue Top | Product appears with correct name, price, and quantity = 1. | Product added successfully. | Product added correctly with accurate details. | Passed | High
[6 empty] | 2. Click Add to Cart. | Quantity: 1
3. Open the cart page.
TC_030 | Cart | REQ_CART_018, REQ_CART_019, REQ_CART_020, REQ_CART_021 | Add multiple products to cart | Verify the user can add multiple products and that totals and quantities calculate correctly. | User browsing product pages. | 1. Add Product A to cart. | Product 1: Blue Top (Qty: 1) | Both products appear with correct details and accurate total. | Products successfully added. | Cart shows all products with correct totals. | Passed | High
[6 empty] | 2. Continue shopping and add Product B. | Product 2: Men T-shirt (Qty: 2)
3. Open the cart page.
TC_031 | Cart | REQ_CART_020, REQ_CART_021 | Update product quantity in cart | Validate that updating item quantity recalculates subtotal and total dynamically. | User already has items in cart. | 1. Open the cart page. | Product: Sleeveless Dress | Subtotal and total recalculate accurately. | Totals update correctly. | Quantity updated and totals recalculated. | Passed | Medium
[6 empty] | 2. Change quantity from 1 to 3. | Initial Qty: 1 → 3
3. Click Update Cart.
TC_032 | Cart | REQ_CART_019, REQ_CART_020, REQ_CART_021, REQ_CART_022 | Remove product from cart | Verify user can remove an item and total updates properly. | User has at least one item in the cart. | 1. Open cart page. | Product: Blue Top (2 items in cart) | Selected product removed; totals recalculated. | Cart updates successfully. | Product removed and totals updated. | Passed | Medium
2. Click Remove (X) next to an item.
3. Confirm removal.
TC_033 | Cart | REQ_CART_017 | Add same product multiple times | Verify adding the same product repeatedly increases its quantity, not duplication. | User on product detail page. | 1. Add the same product twice. | Product: Winter Top (Added twice) | Cart increases product quantity instead of duplicating. | Quantity merged successfully. | Same product quantity updated correctly. | Passed | Medium
2. Open cart.
TC_034 | Cart | REQ_CART_017 | Add product with zero quantity | Verify the system prevents adding an item with quantity = 0. | User on product detail page. | 1. Set quantity to 0. | Product: Blue Top | System displays error or prevents adding. | Action prevented. | Product added with Qty 0 (bug). | Failed | Low
[6 empty] | 2. Click Add to Cart. | Qty: 0
TC_035 | Cart | REQ_CART_019, REQ_CART_023, REQ_CART_024 | Try checkout with empty cart | Verify checkout cannot proceed when cart is empty. | Cart is empty. | 1. Click Cart. | Cart: Empty | System displays “Cart is empty.” Checkout disabled. | User blocked from checkout. | Message displayed; action prevented. | Passed | Medium
2. Try Proceed to Checkout.
TC_036 | Checkout | REQ_CART_025 | Guest checkout restriction | Verify guests must log in or register before checkout. | Guest user with items in cart. | 1. Click Proceed to Checkout. | Guest user | System displays modal asking to Log in or Register. | Checkout restricted. | Guest prompted to sign in before checkout. | Passed | Medium
2. Review login/register prompt.
TC_037 | Checkout | REQ_CART_030 | Invalid payment details | Verify system rejects incorrect payment info. | User on payment form. | 1. Enter invalid card details. | Card: 1234 5678 9012 3456 | Payment fails with error message. | Payment rejected. | Invalid card accepted (bug). | Failed | High
[6 empty] | 2. Click Pay and Confirm. | CVV: 000
TC_038 | Checkout | REQ_CART_026, REQ_CART_027, REQ_CART_029, REQ_CART_031 | Registered user checkout | Verify registered users can complete checkout successfully. | User logged in with saved address. | 1. Add products. | Email: mariamfarghl17@gmail.com | Order placed; confirmation and invoice available. | Order stored successfully. | Order placed and invoice downloaded. | Passed | High
2. Go to checkout.
3. Place order.
TC_039 | Checkout | REQ_CART_026, REQ_CART_027 | Add new shipping address | Verify user can add a new shipping address during checkout. | User logged in. | 1. Click “Add Address.” | Address: 12 El Geish Rd, Alexandria | New address saved and available for order. | Address displayed in checkout. | Feature unavailable (bug). | Failed | Medium
2. Enter details.
3. Save.
TC_040 | Checkout | REQ_CART_030, REQ_CART_031 | Valid payment flow | Verify valid payment completes successfully and order confirmation shown. | Payment gateway simulated. | 1. Select “Credit Card.” | Card: 4111 6093 6531 1791 | Payment success message shown. | Order created successfully. | Payment processed successfully. | Passed | High
[6 empty] | 2. Enter valid data. | CVV: 123
3. Click “Pay and Confirm.”
TC_041 | Checkout | REQ_CART_024 | Cart-to-checkout usability | Validate navigation clarity from cart to checkout on desktop. | User browsing on desktop. | 1. Add items to cart. | Browser: Chrome (Desktop) | “Proceed to Checkout” button visible and functional. | Navigation smooth. | Flow works smoothly. | Passed | Medium
2. Observe layout, button visibility.
TC_042 | Checkout | REQ_CART_030 | Payment field validation | Verify input field restrictions for payment form. | User logged in; at checkout. | 1. Select “Credit Card.” | Name: John123!@# | Invalid entries rejected with validation messages. | Validation prevents submission. | System accepts invalid inputs (bug). | Failed | High
[6 empty] | 2. Enter invalid characters (letters, symbols). | Card: abcdEFGHijkl
[6 empty] | 3. Click “Pay.” | CVV: 12ab
TC_043 | Checkout | REQ_CART_032 | Download invoice | Verify “Download Invoice” button downloads correct file after order placement. | Order completed and confirmation page shown. | 1. Place an order. | Product: Blue Top | PDF invoice downloaded, matches order summary. | Invoice file accessible. | Invoice downloaded with correct details. | Passed | Medium
2. Click “Download Invoice.”
3. Verify downloaded file.
TC_044 | Checkout | REQ_CART_028 | Order comments field | Verify users can add comments or instructions before placing the order. | Cart ready for checkout. | 1. Enter comment in “Order Comments.” | Comment: “Please deliver after 6 PM” | Order placed and comment visible in confirmation or invoice. | Comment saved. | Comments displayed correctly. | Passed | Medium
2. Place order.
3. Check confirmation page.
Shaker Nassry
TC_045 | Catalog | REQ_ADMIN_033 | Admin Login Verification | Verify that admin can successfully log in to the admin panel. | Admin has valid credentials and internet connection. | 1. Go to login page. | Email: admin@yourstore.com | Admin is redirected to dashboard and login succeeds. | Admin navigated to main dashboard. | Admin login successful. | Passed | High
[6 empty] | 2. Enter valid email and password. | Password: admin
3. Click Login.
TC_046 | Catalog | REQ_ADMIN_033 | Add Product with Valid Data | Verify that admin can create a new product using valid inputs. | Admin logged in and on “Add Product” page. | 1. Go to Add Product page. | Name: T‑Shirt | Product created successfully and visible in catalog list. | Product added and stored in database. | Product added and displayed correctly. | Passed | High
[6 empty] | 2. Fill in all required fields (Name, Price, SKU, Category, Image). | Price: 25
[6 empty] | 3. Click Save. | SKU: TSH123
TC_047 | Catalog | REQ_ADMIN_037 | Add Product with Missing Fields | Verify that validation messages appear when mandatory fields are left empty. | Admin logged in. | 1. Go to Add Product page. | Name: Empty | System displays validation errors beside empty fields; product is not created. | Form retains validation messages. | Error shown for “Name” only — bug observed for “Price.” | Failed | High
[6 empty] | 2. Leave “Name” and “Price” empty. | Price: Empty
3. Click Save.
TC_048 | Catalog | REQ_ADMIN_036 | Delete Product | Verify that admin can delete a product from the catalog. | Target product exists in catalog. | 1. Open Catalog section. | N/A | Product removed from catalog list and database. | Product removed permanently. | Deletion successful; product removed. | Passed | High
2. Click Delete next to product.
3. Confirm deletion.
TC_049 | Catalog | REQ_ADMIN_037 | Validate SKU Uniqueness | Verify the system prevents creation of products with duplicate SKU. | Existing SKU already present in system. | 1. Go to Add Product page. | SKU: 1234 | Validation message “SKU already exists” is displayed; duplicate not allowed. | Product not created. | Warning displayed but duplicate product added — bug. | Failed | Medium
2. Enter an existing SKU.
3. Complete other fields.
4. Click Save.
TC_050 | Catalog | REQ_ADMIN_035 / REQ_ADMIN_038 | Update Existing Product Successfully | Verify that admin can modify existing product details and updates sync to frontend. | Admin logged in; product exists. | 1. Open Catalog. | Old Price: 25 → New Price: 30 | Product data updated and visible in both admin and frontend. | Updated information saved. | Product updated successfully. | Passed | High
2. Click Edit.
3. Change product name or price.
4. Click Save.
TC_051 | Catalog | REQ_ADMIN_035 | Update Product with Invalid Data | Verify system prevents updating with invalid data (e.g., negative price). | Admin logged in; product available. | 1. Go to Catalog. | Price: −10 | System displays error “Invalid price value.” Product unchanged. | Product remains with previous data. | Negative value accepted — bug. | Failed | Medium
2. Edit a product.
3. Enter negative price.
4. Save.
TC_052 | Catalog | REQ_ADMIN_034 | View Product List | Verify that admin can view the full catalog with correct product details. | Admin logged in. | 1. Navigate to Catalog. | N/A | Product list displays with all correct details (name, price, category, image). | Product records displayed. | Product list displayed correctly. | Passed | High
2. Scroll through product list.
TC_053 | Catalog | REQ_ADMIN_034 | View Product Details | Verify that admin can open and view product details accurately. | Admin logged in. | 1. Go to Catalog. | N/A | Product details page opens with accurate fields (name, price, image, stock). | Product details accessed. | Product not clickable — bug encountered. | Failed | Medium
2. Click product name or “View.”
TC_054 | Dashboard | REQ_ADMIN_039 | Verify Dashboard Loads Correctly | Ensure that metrics and widgets load properly on dashboard. | Admin logged in. | 1. Log in as admin. | N/A | Dashboard loads with accurate statistics. | Dashboard visible. | Dashboard loaded successfully. | Passed | High
2. Navigate to Dashboard.
3. Observe data and widgets.
TC_055 | Dashboard | REQ_ADMIN_040 | Dashboard Updates After Add | Verify dashboard metrics refresh following product addition. | Admin logged in; dashboard accessible. | 1. Add a new product. | Product: Dress | Product count increases by one. | Updated count displayed. | Dashboard updated correctly. | Passed | High
2. View Dashboard.
3. Check metrics.
TC_056 | Dashboard | REQ_ADMIN_040 | Dashboard Updates After Delete | Verify dashboard metrics decrease after product deletion. | Product already present in system. | 1. Delete an existing product. | N/A | Product count decreases by one. | Updated data reflected. | Dashboard metrics decreased accurately. | Passed | High
2. Open Dashboard.
3. Observe metrics.
TC_057 | Dashboard | REQ_ADMIN_040 | Dashboard Reflects Product Updates | Verify dashboard reflects modifications to product data (e.g., total inventory value). | Admin logged in; product exists. | 1. Update product price or quantity. | Old Price: 25 → 30 | Dashboard accurately shows updated totals. | Dashboard refreshed. | Metrics updated successfully. | Passed | Medium
2. Open Dashboard.
3. Check updated values.
Mohamed Asharf
TC_058 | Performance | REQ_NFR_041 | Homepage Load Speed | Verify that the homepage loads with Largest Contentful Paint (LCP) ≤ 3 seconds. | Website accessible via standard broadband. | 1. Open homepage. | N/A | LCP ≤ 3 seconds. | Website remains stable post‑load. | LCP ≈ 2.7 s — within threshold. | Passed | High
2. Run Lighthouse audit.
3. Record LCP value.
TC_059 | Performance | REQ_NFR_041 | Product Page Load Speed | Verify product listing pages load within 3 seconds. | Browser cache cleared. | 1. Navigate to “Products.” | N/A | Page load time ≤ 3 seconds. | Product pages render correctly. | Product page load ≈ 2.9 s — acceptable. | Passed | High
2. Measure with Lighthouse.
TC_060 | Performance | REQ_NFR_042 | Search Response Time | Verify search results appear within 2 seconds. | Site accessible and search bar functional. | 1. Enter “T‑shirt” in search. | Query: “T‑shirt” | Results load ≤ 2 seconds; relevant listings appear. | Search returns items. | Average result time ≈ 1.4 s. | Passed | High
2. Start timer until results displayed.
TC_061 | Performance | REQ_NFR_043 | API Response Time | Verify that average API response time is below 500 ms. | Developer tools → Network tab open. | 1. Load several pages. | N/A | All API requests respond ≤ 500 ms. | APIs logged. | Most requests ≈ 700–800 ms — exceeds target. | Failed | High
2. Observe API response durations.
TC_062 | Usability | REQ_NFR_044 | Verify Global Navigation | Ensure consistent header, footer, and sidebar across all pages. | Website functional. | 1. Open Home, Products, Contact, Cart pages. | N/A | Header/footer identical across pages; links functional. | Navigation consistent. | Verified visually — consistent across pages. | Passed | High
2. Compare layout.
TC_063 | Usability | REQ_NFR_044 | Verify Category Navigation | Validate each category link routes to the correct page. | User logged in. | 1. Hover over navigation bar. | N/A | Each category link directs to correct page. | Navigation working as designed. | All category links function correctly. | Passed | Medium
2. Click each category.
3. Confirm correct content loads.
TC_064 | Usability | REQ_NFR_045 | Button Hover Feedback | Verify hover effects on clickable buttons. | User on any site page. | 1. Hover over major CTAs. | N/A | Buttons show visible visual change on hover/focus. | Buttons respond interactively. | Hover/focus states working properly. | Passed | Medium
2. Observe style changes (color, shadow, cursor).
TC_065 | Usability | REQ_NFR_045 | Input Focus Indication | Verify that input fields show active focus indication. | A form is visible. | 1. Click inside each text input. | N/A | Focused field clearly highlighted. | Form ready for input. | Inputs show appropriate focus outline. | Passed | Medium
2. Observe border/highlight.
TC_066 | Usability | REQ_NFR_046 | Responsive Desktop Layout | Verify site layout and alignment on desktop view. | Browser at 1920 × 1080 resolution. | 1. Load homepage. | N/A | No overlap; correct alignment of all sections. | Desktop layout validated. | Layout displays properly on desktop. | Passed | High
2. Review content alignment.
TC_067 | Usability | REQ_NFR_046 | Responsive Mobile Layout | Validate responsive design on mobile screens. | Viewport 375 × 667 or mobile emulator. | 1. Open site on mobile. | N/A | No content cut‑off or horizontal scrolls. | Responsive layout confirmed. | Clean and usable mobile layout. | Passed | High
2. Verify readability & element stacking.
TC_068 | Usability | REQ_NFR_047 | Validation Error Messages | Verify clarity and placement of inline validation messages. | Form with mandatory fields accessible. | 1. Leave one required field blank. | Invalid input | Clear, descriptive error shown beside field. | Validation feedback displayed. | “Field required” shown correctly. | Passed | High
2. Submit form.
3. Observe error message.
TC_069 | Accessibility | REQ_NFR_048 | Keyboard Navigation | Verify full navigation usability via keyboard. | Keyboard connected. | 1. Use Tab key to move through UI. | N/A | All links/forms accessible via keyboard; logical order maintained. | Accessibility validated. | Keyboard navigation works for all elements. | Passed | High
2. Activate elements using Enter.
TC_070 | Accessibility | REQ_NFR_048 | Accessibility Audit | Assess WCAG 2.1 AA compliance using accessibility tools. | AXE or WAVE extension installed. | 1. Run automated accessibility audit. | N/A | No critical WCAG 2.1 AA issues. | Audit results stored. | ARIA labels missing; minor contrast errors → bug. | Failed | High
2. Review results for ARIA, contrast, alt attributes.
TC_071 | Security | REQ_NFR_049 | HTTPS Encryption Verification | Verify HTTPS/TLS encryption is active site‑wide. | Browser available. | 1. Visit https://automationexercise.com. | N/A | HTTPS active with valid certificate; no mixed content. | Connection remains secure. | HTTPS verified via valid Cloudflare SSL. | Passed | High
2. Check padlock/SSL cert validity.
TC_072 | Security | REQ_NFR_050 | XSS Vulnerability Test | Verify that user inputs are sanitized against script injection. | Input form available. | 1. Enter harmless JS snippet in input. | <script>alert('XSS')</script> | Script ignored; no alert executes. | Application secured. | Script blocked successfully. | Passed | High
2. Submit form.
TC_073 | Security | REQ_NFR_050 | SQL Injection Test | Verify input fields sanitize SQL injections. | Input form accessible. | 1. Enter ' OR 1=1 -- in form. | ' OR 1=1 -- | No SQL errors or unauthorized data exposure. | Application remains stable. | Input sanitized; attack failed. | Passed | High
2. Submit form.
TC_074 | Compatibility | REQ_NFR_051 | Chrome Browser Functionality | Verify full functionality on Google Chrome. | Chrome installed and updated. | 1. Open website. | N/A | No rendering or console errors in Chrome. | All UI elements functional. | All features work as expected. | Passed | High
2. Perform complete shopping flow.
TC_075 | Compatibility | REQ_NFR_051 | Safari Browser Layout Validation | Verify UI consistency on Safari browser. | Safari v17 installed. | 1. Open website. | N/A | Layout and spacing consistent with baseline. | Cross‑browser report created. | Minor spacing issues observed (bug). | Failed | Medium
2. Inspect visual layout.
TC_076 | Compatibility | REQ_NFR_052 | Add‑to‑Cart JS Functionality | Verify dynamic “Add to Cart” works with JavaScript enabled. | Browser with JS enabled. | 1. Add an item to cart. | Product Item | Cart count updates dynamically; no reload needed. | Cart reflects new item. | Cart icon updated immediately. | Passed | High
2. Observe UI update.
TC_077 | Compatibility | REQ_NFR_052 | Checkout Dynamic Functionality | Verify checkout page updates dynamically with JS actions. | Logged‑in user with cart items. | 1. Open Checkout page. | JS runtime active | Changes reflected instantly without page reload. | Checkout remains responsive. | Functions smooth; no errors logged. | Passed | High
2. Change item qty/remove item.
3. Observe live update.

## Traceability
Req_ID | Linked_UserStories | Linked_TestCases
REQ_AUTH_001 | US_001 | TC_001, TC_002, TC_003
REQ_AUTH_002 | US_002 | TC_004, TC_005
REQ_AUTH_003 | US_003 | TC_006, TC_007
REQ_AUTH_004 | US_004 | TC_008
REQ_AUTH_005 | US_005 | TC_009, TC_010
REQ_AUTH_006 | US_006 | TC_011, TC_012
REQ_AUTH_007 | US_007 | TC_013, TC_014, TC_015
REQ_PROD_008 | US_008 | TC_016
REQ_PROD_009 | US_009 | TC_017
REQ_PROD_010 | US_010 | TC_018
REQ_PROD_011 | US_011 | TC_019, TC_020
REQ_PROD_012 | US_012 | TC_021, TC_022
REQ_PROD_013 | US_013 | TC_023
REQ_PROD_014 | US_014 | TC_024, TC_025, TC_026
REQ_PROD_015 | US_015 | TC_027
REQ_PROD_016 | US_016 | TC_028
REQ_CART_017 | US_017 | TC_029, TC_033, TC_034
REQ_CART_018 | US_018 | TC_030
REQ_CART_019 | US_019 | TC_030, TC_032, TC_035
REQ_CART_020 | US_020 | TC_030, TC_031, TC_032
REQ_CART_021 | US_021 | TC_030, TC_031, TC_032
REQ_CART_022 | US_022 | TC_032
REQ_CART_023 | US_023 | TC_035
REQ_CART_024 | US_024 | TC_035, TC_041
REQ_CART_025 | US_025 | TC_036
REQ_CART_026 | US_026 | TC_038, TC_039
REQ_CART_027 | US_027 | TC_038, TC_039
REQ_CART_028 | US_028 | TC_044
REQ_CART_029 | US_029 | TC_038
REQ_CART_030 | US_030 | TC_037, TC_040, TC_042
REQ_CART_031 | US_031 | TC_038, TC_040
REQ_CART_032 | US_032 | TC_043
REQ_ADMIN_033 | US_033 | TC_045, TC_046
REQ_ADMIN_034 | US_034 | TC_052, TC_053
REQ_ADMIN_035 | US_035 | TC_050, TC_051
REQ_ADMIN_036 | US_036 | TC_048
REQ_ADMIN_037 | US_037 | TC_047, TC_049
REQ_ADMIN_038 | US_038 | TC_050
REQ_ADMIN_039 | US_039 | TC_054
REQ_ADMIN_040 | US_040 | TC_055, TC_056, TC_057
REQ_NFR_041 | US_041 | TC_058, TC_059
REQ_NFR_042 | US_042 | TC_060
REQ_NFR_043 | US_043 | TC_061
REQ_NFR_044 | US_044 | TC_062, TC_063
REQ_NFR_045 | US_045 | TC_064, TC_065
REQ_NFR_046 | US_046 | TC_066, TC_067
REQ_NFR_047 | US_047 | TC_068
REQ_NFR_048 | US_048 | TC_069, TC_070
REQ_NFR_049 | US_049 | TC_071
REQ_NFR_050 | US_050 | TC_072, TC_073
REQ_NFR_051 | US_051 | TC_074, TC_075
REQ_NFR_052 | US_052 | TC_076, TC_077

## Bug_Report
Bug ID | Module / Feature | Title / Summary | Reported By | Detected In / Test Cycle | Severity | Priority | Environment | TC_ID | Req_ID/US_ID | Description | Steps to Reproduce | Expected Result | Actual Result | Status | Assigned To | Detected By
BUG‑001 | Auth / Forgot Password | Forgot Password feature not implemented | EA | Cycle 1 | Major (Missing Functionality) | High | QA Staging | TC_006 / US_003 | REQ_AUTH_003 | “Forgot Password” link visible but feature not working; no reset email sent. | 1. Open Login page. | Password reset link sent to email. | Feature not implemented; no email sent. | New (Confirmed Bug) | Dev Team | EA
2. Click Forgot Password.
3. Enter valid email & submit.
BUG‑002 | Auth / Forgot Password | Unregistered email lacks “Email not found” notice | EA | Cycle 1 | Minor (Validation) | Medium | QA Staging | TC_007 / US_003 | REQ_AUTH_003 | No user feedback when password reset attempted with unregistered email. | 1. Click Forgot Password. | Message “Email not found.” | No message displayed; request fails silently. | New (Confirmed Bug) | Dev Team / UI | EA
2. Enter fake email (e.g., none@mail.com).
BUG‑003 | Auth / Change Password | “Change Password” option missing under My Account | EA | Cycle 1 | Major (Missing Feature) | High | QA Staging | TC_010 / US_005 | REQ_AUTH_005 | Section to update password not available post‑login. | 1. Login as user. | Option to change password exists and works. | No “Change Password” button present. | New (Confirmed Gap) | Dev Team | EA
2. Navigate to My Account.
BUG‑004 | Product / Sorting | Sorting by Price (Low → High) not implemented | EA | Cycle 2 | Major (Missing Function) | Medium | QA Staging | TC_019 / US_011 | REQ_PROD_011 | Sorting option available but non‑functional. | 1. Open category page. | Products reorder correctly. | No price sorting applied. | New | Dev Team | EA
2. Select “Price: Low → High.”
BUG‑005 | Product / Sorting | Sorting by Price (High → Low) not implemented | EA | Cycle 3 | Major | Medium | QA Staging | TC_020 / US_011 | REQ_PROD_011 | “Price: High → Low” feature not working. | 1. Open category page. | List orders by highest price. | Sorting missing. | New | Dev Team | EA
2. Select “High → Low.”
BUG‑006 | Product / Price Filter | Price‑Range Filter Not Available in System | EA | Cycle 4 | Major | Medium | QA Staging | TC_021 / US_012 | REQ_PROD_012 | Filtering by price range missing or non‑functional. | Attempt filter products by range 200–500. | Only products in range display. | Filter option not available. | New | Dev Team | EA
BUG‑007 | Product / Brand Search | Search returns partial brand results | EA | Cycle 1 | Moderate (Data) | Medium | QA Staging | TC_026 / US_014 | REQ_PROD_014 | Not all items of brand “Polo” appear in search results. | 1. Enter “Polo” in search bar. | All Polo branded products displayed. | Some products missing from results. | New (Data Mismatch) | Dev Team | EA
BUG‑008 | Product / Random Search | Missing “No Products Found” message for empty results | EA | Cycle 1 | Minor (UI Feedback) | Medium | QA Staging | TC_027 / US_015 | REQ_PROD_015 | When no items match search, system shows blank page without message. | 1. Search for “abcxyz.” | Show “No products found.” | Page blank; no message displayed. | New (Confirmed Bug) | Dev Team | EA
BUG‑009 | Product / Layout Toggle | Grid/List toggle buttons missing from UI | EA | Cycle 6 | Minor (Missing Feature) | Low | QA Staging | TC_023 / US_013 | REQ_PROD_013 | View options for Grid vs List not implemented. | Try switching to List View. | Layout changes appropriately. | Toggle not available. | New | Dev Team | EA
BUG‑010 | Cart / Add to Cart | Product added with Quantity = 0 and price = 0 | Mariam Farghl | Cycle 1 | Critical (Data Integrity) | High | QA Staging | TC_034 / US_CART_017 | REQ_CART_017 | System allows invalid zero‑quantity additions to cart. | Set quantity 0 → Add to Cart. | System blocks action with error. | Product added successfully with Qty 0. | New (Confirmed Bug) | Dev Team | Mariam Farghl
BUG‑011 | Cart / Payment | Invalid Card Accepted as Successful Payment | Mariam Farghl | Cycle 1 | Critical (Security/Data Validation) | High | QA Staging | TC_037 / US_CHK_030 | REQ_CART_030 | Payment form accepts fake card data and places order. | Use invalid card details. | Order denied; error shown. | Order placed successfully. | New (Confirmed Bug) | Dev Team | Mariam Farghl
BUG‑012 | Admin Catalog / Product | Product Added Without Price Validation | SF | Cycle 1 | Major (Validation) | High | QA Staging | TC_047 / US_037 | REQ_ADMIN_037 | Price field not mandatory; product added without price. | Leave Price empty on Add Product. | Save blocked. | Product saved without price. | New (Confirmed Bug) | Dev Team | SF
BUG‑013 | Admin Catalog / SKU Validation | Duplicate SKU Allowed Despite Warning | SF | Cycle 1 | Major (Data Integrity) | Medium | QA Staging | TC_049 / US_037 | REQ_ADMIN_037 | System shows warning but still adds duplicate SKU. | Add product with existing SKU. | Save blocked. | Product with duplicate SKU created. | New (Confirmed Bug) | Dev Team | SF
BUG‑014 | Admin Catalog / Edit | Negative Price Accepted on Update | SF | Cycle 1 | Major (Input Validation) | Medium | QA Staging | TC_051 / US_035 | REQ_ADMIN_035 | Negative price values allowed on Edit Product. | Edit → set price −10 → Save. | Show error “Invalid price.” | Product updated with −10 price. | New (Confirmed Bug) | Dev Team | SF
BUG‑015 | Admin Catalog / UI | Product Details Links Not Clickable in List | SF | Cycle 1 | Minor (UI Flow) | Medium | QA Staging | TC_053 / US_034 | REQ_ADMIN_034 | Product list items do not open details page. | Click product name → expected to open. | Product details page opens. | Click inactive; no redirect. | New (Confirmed Bug) | Dev Team | SF
BUG‑016 | NFR / Accessibility | Accessibility fails ARIA & contrast checks | MA | Cycle 1 | Major (Compliance) | High | QA Staging | TC_070 / US_048 | REQ_NFR_048 | Audit reported missing ARIA labels and low contrast text. | Run AXE/WAVE audit. | Pass WCAG 2.1 AA. | Multiple issues flagged. | New | Dev Team | MA
BUG‑017 | NFR / Performance API | API Response > 500 ms Threshold | MA | Cycle 1 | Major (Performance) | High | QA Staging | TC_061 / US_043 | REQ_NFR_043 | Average API timings exceed limit (~700–800 ms). | Load site → open DevTools Network. | API < 500 ms. | Responses > limit. | New | Dev Team | MA
BUG‑018 | NFR / Compatibility Safari | Layout Misalignment on Safari | MA | Cycle 1 | Minor (UI Aesthetic) | Medium | QA Staging | TC_075 / US_051 | REQ_NFR_051 | Spacing differs slightly in Safari layout. | Open site in Safari v17. | UI consistent with other browsers. | Spacing mismatch present. | New | Dev Team | MA
🔹 Validation Summary by Mo

## Summary_Report
Coverage Summary |  |  |  |  | BUG Report Summary
Module | Requirements | User Stories | Test Cases | Coverage Status | Module / Feature Area | No. of Bugs | % of Total | Comment
Authentication | 7 | 7 | 15 | 100% Coverage | Authentication | 3 | 17 % | Missing features (Forgot Password, Change Password)
Product / Frontend | 9 | 9 | 13 | 100% Coverage | Product / Frontend | 6 | 33 % | Sorting + Filtering + Search defects (missing features Sorting / Filtering )
Cart / Checkout | 16 | 16 | 16 | 100% Coverage | Cart / Checkout | 2 | 11 % | Data validation / Payment flow
Admin / Dashboard | 8 | 8 | 13 | 100% Coverage | Admin / Dashboard | 4 | 22 % | Input validation / UI navigation
Non‑Functional | 12 | 12 | 20 | 100% Coverage | Non‑Functional (NFR) | 3 | 17 % | Accessibility / Performance / Browser compatibility
➡ Total | 52 Requirements | 52 Stories | 77 Test Cases | 100 % Traceability Achieved | Total | 18 | 100%